## Inspection Findings
Black Bull Green Play Area — Operational Inspection Report
Langtoft Parish Council (Lincolnshire) ¦ Inspected: 22 April 2026 ¦ Inspector: John-Aris Hirst (RPII Annual Inspector) ¦ Overall Site Risk: 9 — Low Risk
Equipment / Item | Manufacturer | Surface Type | Risk Rating | Risk Score | Recommended Actions
Site general (surfaces) | Owner/Operator | N/A | Low | 8 | 1. Remove trip hazards at surface edges 2. Lift and re-glue lifting tiles to secure 3. Monitor gaps between tiles; repair as required 4. Remove weed/vegetation growth from surfaces
Sign (entrance) | Not identified | Grass | Very Low | 4 | Satisfactory — no work required
Gate — self closing (×2) | Not identified | Tarmac | Low | 6 | 1. Treat rusted/corroded areas and repaint 2. Adjust gate to close within 4–8 seconds
Gate — maintenance | Not identified | Grass | Not assessed | N/A | 1. Full assessment not possible (padlocked) — ensure 12 mm gaps throughout full range of motion 2. Treat rusted/corroded areas and repaint 3. Provide 12 mm gap at both sides of gate throughout full range of motion to prevent finger trapping
Fence — bow top | Not identified | Grass | Low | 6 | Treat rusted/corroded areas and repaint
Bench | Not identified | Mixed surface | Low | 6 | Item damaged — monitor for further deterioration and replace as required
Picnic table | Not identified | Grass | Low | 8 | Secure table to the ground (currently unsecured within falling space of equipment)
Litter bin (Broxap) | Broxap | Grass | Low | 8 | Secure bin to the ground to prevent tipping or rolling
Litter bin — dog shaped (Glasdon) | Glasdon | Grass | Low | 8 | 1. Secure bin to the ground to prevent tipping or rolling 2. Empty bin and review collection routine
See saw | Hags | Rubber tiles | Low | 8 | 1. Replace missing/damaged bolt cap covers 2. Monitor seat damage and replace as required 3. Replace all missing fixings 4. Treat rusting spring components and repaint
Swings — 1 bay (cradle + flat seat) | Hags | Rubber tiles | Low | 6 | 1. Treat rusted/corroded framework and repaint 2. Monitor chain wear; replace when 40% worn 3. Monitor seat damage and replace as required 4. Lubricate Anti Wrap bearings per manufacturer guidance
Multi play (junior) | Hags | Rubber tiles | Low | 9 | 1. Monitor shackle wear; replace when 40% worn 2. Monitor connecting lug wear; repair as required 3. Monitor corroding shackles; replace as required 4. Remove rough edges from dented slide surface; monitor and repair 5. Inspect ropes concealed by tape for broken wire strands; repair or replace 6. Monitor worn/damaged ropes and nets; repair or replace as required 7. Remove graffiti
Spring hippo | Hags | Rubber tiles | Very Low | 6 | 1. Replace missing/damaged bolt cap covers 2. Monitor seat damage and replace as required
Spring cat | Hags | Rubber tiles | Very Low | 6 | 1. Replace missing/damaged bolt cap covers 2. Monitor seat damage and replace as required 3. Replace missing end caps on handgrips/footrests
Sign (internal) | Not identified | Grass | Very Low | 4 | Satisfactory — no work required
Rider (outdoor fitness) | Fresh Air Fitness | Grass matrix tiles | Low | 8 | Replace missing/damaged bolt cap covers
Rower (outdoor fitness) | Fresh Air Fitness | Grass matrix tiles | Low | 8 | 1. Replace missing/damaged bolt cap covers 2. Investigate internal corrosion from water retention; repair as required
Air walker (outdoor fitness) | Fresh Air Fitness | Grass matrix tiles | Low | 8 | Satisfactory — no work required
5-a-side goals (×2) | Not identified | Grass | Not assessed | N/A | 1. Implement full load testing (outside inspection scope) 2. Repair or replace damaged framework 3. Secure nets 4. Monitor loose foundations; repair as required 5. Replace cable ties with appropriate fixings (sharp projecting ends present) 6. Repair or replace damaged nets