## Inspection Findings
East End Park — Operational Inspection Report
Langtoft Parish Council (Lincolnshire) ¦ Inspected: 22 April 2026 ¦ Inspector: John-Aris Hirst (RPII) ¦ Overall site risk: 12 — Moderate
Equipment / Item | Manufacturer | Risk Score | Risk Level | Recommended Actions
Site general (surfaces & grounds) | Owner/Operator | 8 | Low | • Remove weed/vegetation growth • Remove trip hazards at surface edges • Monitor safety surface wear and repair as required • Monitor and repair gaps between surfacing and edging • Clean and treat algae/moss causing slippery conditions • Obtain specialist water safety risk assessment for nearby water body (contact RLSS)
Sign (playground) | Not identified | 4 | Very Low | • No action required — satisfactory
Gate — self-closing | Not identified | 10 | Low | • Reinstate eroded area under gate to level with surrounding surfaces • Provide 12 mm gap throughout full range of motion on both sides • Adjust gate closing speed to between 4 and 8 seconds • Secure gate to hinges — can currently be lifted off
Gate — maintenance | Not identified | 8 | Low | • Ensure 12 mm gaps throughout full range of motion (padlocked at inspection, could not be fully assessed) • Provide 12 mm gap throughout full range of motion on both sides • Repair failed welds
Stile | Not identified | 8 | Low | • Clean and treat algae/moss • Monitor strimmer damage on posts and replace if rot develops • Monitor timber splits/shakes; sand rough edges; ensure splits do not cross fixing points • Reinstate eroded area around base
Fencing — timber | Not identified | 8 | Low | • Monitor loose posts and reset as required • Replace all rotted timber sections
Fence — chainlink | Not identified | 8 | Low | • Remove cable ties with sharp projecting ends • Monitor corroding mesh and replace as required
Bench ×2 (grass surface) | Not identified | 8 | Low | • Treat rusting/corroding metalwork and repaint • Replace all missing fixings
Bench (paving slabs) | Not identified | 4 | Very Low | • No action required — satisfactory
Picnic tables ×2 | Not identified | 8 | Low | • Monitor fire damage and repair as required • Monitor general damage and replace as required • Remove excess projecting bolt thread lengths or fit caps
Litter bin | Not identified | 8 | Low | • Secure bin to the ground to prevent tipping or rolling
Activity trail | A.E. Evans | 10 | Low | • Monitor timber splits/shakes; sand rough edges; ensure splits do not cross fixing points • Replace missing or damaged bolt cap covers • Monitor timber rot and replace as required • Monitor strimmer damage on posts; replace if rot develops • Clean and treat algae/moss • Adjust bridge so it does not contact the surface under load • Monitor swing step foundation — slightly loose • Tighten fixings or replace timber parts where splits run through fixing points
Slide unit | Not identified | 9 | Low | • Monitor south-facing slide surface temperature in hot weather • Monitor and repair dents in slide surface • Monitor and repair damaged slide side • Replace all missing fixings • Replace all rotted timber sections • Reinstall loose bench to secure • Monitor and repair gaps between surfacing and edging • Monitor fire damage to surfacing • Repair split in slide surface • Remove graffiti
Tyre trail | Not identified | 9 | Low | • Replace damaged tyres • Reinstate grass in impact area or provide all-weather surface • Monitor perishing rubber and replace as required
1 Bay 2 Seat swing — cradle | Wicksteed Playgrounds | 6 | Low | • Rub down and repaint flaking metalwork • Monitor and repair gaps between surfacing and edging • Monitor seat damage/wear and replace as required
Misc springer | Not identified | 6 | Low | • Rub down and repaint flaking metalwork • Inspect ropes beneath tape and repair or replace as required • Monitor worn/damaged ropes and nets; repair or replace • Treat rusting spring components and repaint • Secure all loose fixings
Table tennis | Cornilleau | 8 | Low | • Remove excess projecting bolt thread lengths or fit caps • Replace all missing fixings
See-saw | Wicksteed Playgrounds | 10 | Low | • Replace damaged gaiter • Replace severely damaged seats • Treat rusting/corroding metalwork and repaint • Repair damaged surfacing • Treat and repair perforated/excessively corroded steel sections • Monitor worn mechanism and replace as required
2 Bay 4 Seat swing | Wicksteed Playgrounds | 12 | Moderate | • Inspect upper fixings/components per manufacturer recommendations (above 2.5 m, not fully accessible) • Cut back excess chain tails, retaining minimum 2 links through crucifix connectors • Replace excessively worn chain links — PRIORITY • Monitor shackle wear and replace when 40% worn • Tighten loose swing seat connectors • Monitor crucifix connections and replace as required • Rub down and repaint flaking metalwork • Monitor and repair gaps between surfacing and edging • Monitor minor surface damage • Monitor seat damage/wear and replace as required
Ball shoot | Not identified | 6 | Low | • Clean and treat algae/moss
Cable runway (zip wire) | Not identified | 12 | Moderate | • Remove excess projecting bolt thread lengths or fit caps • Inspect main cable, suspension links and fixings per manufacturer recommendations — PRIORITY • Replace all rotted timber platform sections (exposing sharp screws) • Replace missing components • Replace all missing fixings • Replace all further rotted timber sections • Replace missing/damaged post or end caps • Remove weed/vegetation growth from surface • Provide more suitable isolation method — current cordon still accessible and introducing hazards — PRIORITY • Secure the traveller or remove it (seat and suspension missing — client notified) — PRIORITY • Remove all rough/splintered timber edges • Secure all loose fixings • Re-stain all affected timber with appropriate preservative
5-a-side goals ×2 | Not identified | 8 | Low | • Arrange formal load testing of goals (outside inspection scope) • Reinstate eroded ground surface (slippery in wet conditions) • Monitor loose foundations and repair as required • Monitor distortion damage and replace as required • Replace cable ties with a more appropriate fixing method • Repair or replace damaged nets
Fitness sign | Fresh Air Fitness | 6 | Low | • Monitor slightly loose foundations and repair as required
Air skier | Fresh Air Fitness | 8 | Low | • Monitor bearing wear and replace as required
Combination unit | Fresh Air Fitness | 8 | Low | • Treat rusting/corroding metalwork and repaint
Push up / dip station | Fresh Air Fitness | 8 | Low | • No action required — satisfactory

## Legend
Risk Level Key
Moderate (score 12+) | Significant concern — action required promptly
Low (score 6–11) | Routine maintenance required — monitor and schedule
Very Low (score 1–5) | Minor or no issues — satisfactory or monitor only
Score calculation
Risk score = Likelihood (1–5) × Severity (1–5)