## Actions
Langtoft Parish Council Action tracker
Key:
In progress
Date added | Location | Task | Who is responsible | Deadline | Notes | Column1
| West end Manor close | Repair and repaint bench
| Crossroads | Wood preserve the noticeboard
2026-01-01 | East end park | Consider wheelchair access
2026-07-01 | Parks, Cemetery, Penfield | Update contact information on signage | Clerk |  | Waiting on Penfield requirements
2026-05-01 | N/A | Arrange code of conduct training for cllrs | Clerk |  | Details shared 19/8/26
2026-07-01 | Parks | Consider 'all dogs must be kept on a lead' signage | All
2026-02-01 | Crossroads | Request from resident for a permant christmas tree to be planted at the crossroads |  |  | Elderwood chased 17/8
2026-02-01 | N/A | To consider and adopt new communication policy | All
2025-06-01 | N/A | Draw up a list of preferred suppiers | Cllrs Tatam, Carter and the Clerk
2026-04-01 | EEP | Football at EEP | Bev |  | Follow up legal advice
| N/A | Financial policy | All |  | draft policy on file finance to look at and approve
| Village hall | Land registry - see attached note | Clerk/ village hall |  | Land to be registered
2025-08-01 | Crossroads pavement | Needs resurfacing | Clerk |  | Reported to Dan Head of Highways onsite meeting 30/8 chased again 23/9/25. Cllr Dilks (PCM 7th July) advised works date of 16th October
| Stowe road | Geese signs | Cllr V Smith |  | Vanessa chasing SKDC for 2 further signs
| Manor close | Residents parking permits - see note |  |  | PC to meet with school awaiting outcome from LCC Highways
| Ash close/ shop | Extra bin to be installed |  |  | Daniel Barker and Anthony Coe has confirmed an extra bin for a location between Ash Close and the Shop once an assessement by SKDC has taken place
| Teal way | Grit bin - A request has been made to SKDC for an additional grit bin on the entrance to the new Teal Way development |  |  | 2/3 Tim Hunter LCC Highways has looked into this. Teal Way has not yet been adopted by LCC, it is unlikely that this location would qualify for an LCC grit bin. Once adopted (possibily 1 years time) an application can be reconsidered. | PC to consider if they wish to purchase their own grit bin for this location.
2026-04-01 | Asstd | Relocate SIDs signs to increase impact | Cllr. Scott
| Pavillion park | Coronation tree grant | Pete Coles, Liz Jarman |  | Apply for funding for fruit trees for pavilion Park
2026-07-01 | Task allocation | Tasks are being missed | All |  | Allocate tasks between PCMs
2026-07-01 | Quarryworks | Mop highlighted that the quarryworks may affect air quality | Cllr. Farrington |  | Speak to cllr. Smith about air quality surveys
2026-07-01 | N/A | Add all cllrs to bank to approve transactions | Clerk |  | Forms to be completed at PCM - 15/9/26 | Forms prepared for 15/9
2026-07-01 |  | Dog waste bin to be removed and disposed of (including those in the Penfield containers) | Cllr Tatam
2026-07-01 | N/A | Recruitment - we now only have 6 cllrs | All |  | Ask school to contact parents about recruitment and ask mop's
2026-07-01 | BBG park | The BBG hedge needs a contractor to get it back under control | Clerk |  | Quotes requested
| EEP | Pedestrian gate | Gardener |  | Pedestrian Gate not closing between 4-8 seconds & adjust knock inprotruding nails check timbers secure
| EEP | Bin not securred to the ground | Clerk |  | SKDC bin, reported on Fix my street
| EEP | Metal gate welding failed |  |  | Gate is locked
| EEP | Slide - Step replace rotten timbers to complete covering of bolt threads with caps | Cllr. Branch
| EEP | Tyres - reseed worn areas, monitor growth and reseed if necessary | Gardener
2026-09-03 | EEP | The culvert at the footpath entrance to the park should be fenced. |  |  | PRIORITY 1 - imminent danger | P Coles proposed a hedge
2026-09-03 | EE Pond | “Danger, Risk of falling” sign on each of the culvert fences |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EEP | Footpath entrance to EEP - Danger Deep Water, children should be supervised at all times |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EEP | 3 park entrances: “Deep Water”, “Uneven Ground” and “Risk of falling” |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EEP | 3 park entrances: mandatory (white on blue) notice that “Children should be supervised at all times” |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EEP | 3 park entrances: information sign (green background with white text and symbols) “In the event of a person falling into the water, DIAL 999 and ask for the FIRE BRIGADE”. The sign should also quote the relevant What3Words location. |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EE Pond | Two “Danger Deep Water”, “Uneven Ground”, “Children should be supervised at all times” signs should be installed on the knee high, single bar rustic fence, and on the edge of the pond near the footpath entrance. |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EE Pond | “Danger, Risk of falling”, “Danger Deep Water”, “Uneven Ground”, “Children should be supervised at all times” sign should be installed on the “Log Pile”. |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EE Pond | “Danger, Risk of falling”, “Children should be supervised at all times” signage should be installed on the two culvert fences. |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EE Pond | An information sign (green background with white text and symbols) should be mounted on the lifebuoy stand stating, “In the event of a person falling into the water, DIAL 999 and ask for the FIRE BRIGADE”. The sign should also quote the What3Words location “///reports.condensed.springing”. |  |  | PRIORITY 2 - significant hazard
2026-09-03 | EE Pond | side of the pond furthest from the play areas has accessible banks 10 metres from a public footpath. Consider a knee high, single bar rustic fence to deter access |  |  | PRIORITY 3 - safety recommendation
2026-09-03 | Penfield | An Ash tree displaying a weak fork was observed close to a path. This is not an immediate concern but would benefit from monitoring and, where appropriate, future management — particularly as this tree is close to one of the paths |  |  | See tree survey for image reference
2026-09-03 | Cemetery | Tree 4 - possibly dead |  |  |  | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Front hedge - Front, top and sides need cutting back |  |  |  | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Tree 4 - remove stake |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Tree 10 - Lift crown to 2 metres |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Tree 11 - Lift crown to 2 metres |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Tree 12 - Lift crown to 2 metres |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Tree 15 - Lift crown to 2 metres |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Tree 23 - Lift crown to 2 metres |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | BBG Park | Tree 24 - Lift crown to 2 metres |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 1 - Lift crown to 2.5 metres |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 8 - Lift crown to 2.5 metres |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 10 - Lift crown to 2.5 metres |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 16 - Remove deadwood over 25mm dia. |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 22 - Fell |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 24 - Sever Ivy at base |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 26 - Sever Ivy at base |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 27 - Sever Ivy at base |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 28 - Fell |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 29 - Sever Ivy at base |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 31 - Remove deadwood over 25mm dia. |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 32 - Lift crown to 2.5 metres |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 36 - Remove deadwood over 25mm dia. |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 38 - Lift crown to 2.5 metres |  | Mar-Jun 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 55 - Sever Ivy at base |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 57 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 58 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 60 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 68 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 72 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 79 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 80 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 97 - Sever Ivy at base |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 115 - Remove deadwood over 25mm dia. |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 116 - Sever Ivy at base |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 117 - Sever Ivy at base |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 118 - Remove deadwood over 25mm dia. And sever ivy at base |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | EEP | Tree 119 - Sever Ivy at base and remove arisings from base |  | Jun-Dec 26 | Survey completed 31/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | Cemetery | Tree 27 - Sever Ivy at base |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-09-03 | Cemetery | Tree 29 - Remove stake |  | Jun-Dec 26 | Survey completed 17/12/25 | Tree surgeon needed - clerk to get quotes
2026-05-11 | Website | Clerk to update: a) Standing Orders b) Financial Regulations c) Fixed Asset Register d) SKDC Code of Conduct e) Risk Assessment f) Document Retention Policy | Clerk | asap
2026-07-01 | EEP | HIGH RISK - activity trail | Full council | asap | See p12 of inspection from 28/8/26 All rotten timbers need replacing, fixings need tightening, swing step is loose, replace missing bolt caps
2026-07-01 | EEP | Cableway fixing are loose | Full council | asap | Clerk to get repair quotes
Note on C17: Nick Scutt Solicitor retired 31 May:-a. We currently hold the unregistered title deeds of which Land Registry have made their own scanned copies before returning those deeds to us (and probably best that we hang onto them until the first registration is complete in case of any queries) b. We’ve sought/claimed title to the unregistered ramp area to the right of the building even though the attached 1972 conveyance with its plan records a narrower frontage and we will wait to see what LR decidec. c)The Parish Council continues to hold the land as bare trustee for the Langtoft Village Hall (a registered charity) and restrictions to that effect should appear in the new title register.
Note on C20: To meet with school to discuss school policing drop and collection with regards to parents parking and child safety To suppor residents with resident permits. Cllr. Dilks and Head of Highways met Lewis Trickey on site. It seems like the lines will be put in place, however Lewis has requested "resident permits".

## Completed tasks
Date added | Location | Task | Who is responsible | Deadline | Notes | Completion date
2026-02-01 | N/A | GDPR help |  |  | Resident has offered to help, 25/2 clerk contacted mop for more information
2026-07-01 | N/A | Simplify action tracker | Clerk | asap |  | 2026-08-01
2026-07-01 | EEP | Add cleaning under slide to gardener's duties | Cllr Tatam |  |  | 2026-07-01
2026-07-01 | N/A | Arrange scribe/ civic.ly demo | Clerk | asap | Prerecorded demo distributed | 2026-08-01
2026-07-01 | N/A | Contact gardeners appraisal | Cllr Tatam | asap |  | 2026-07-01
2026-07-01 | N/A | Check Grapevine submission criteria | Clerk | asap |  | 2026-08-01
| EEP | RLSS risk assessment | Pete Coles |  | Aqua serve | 2025-11-01
| EEP | Bolt caps need replacing on picnic bench | Gardener |  | Gardener has supply of caps
| EEP | Activity trail | Gardener |  | Rotten timbers on A frame to be removed | 2026-08-01
| EEP | Rocker - exposed concrete at entrance. Back fill with soil, install grass mat and reseed. SG to order grass mat and pegs | Gardener/ clerk
| EEP | Cableway - renew cable and seat chain. Make new steps platform | Clerk
| N/A | GDPR help |  |  | Resident has offfered to help, 25/2 clerk contacted mop for more information
| EEP | Seesaw seats broken, gaiter worn, welding required at base |  |  | Agreed 13/7, ordered 14/7 | 2026-08-26
| EEP | 4 base swing - replace chains |  |  | Agreed 13/7, ordered 14/7 | 2026-08-26
2026-07-01 | BBG park | External inspector was delayed, ensure report is received. Expected by 18th August | Clerk |  |  | 2026-08-27
2026-01-01 | West end, Ash close | To source licence from SKDC for new verge side bench to source quotes for consideration | Cllr. McCulloch, gardener |  | 13/1/26 LCC consent received, bench to be ordered and intalled | Unknown, removed 6/9/2026
2024-09-01 | Pub gullies | Gullies blocked, LCC to clear | Clerk |  | reported on fix my street 3/9/24 | Unknown, removed 6/9/2026
| Asstd | Community speed watch | Chris Palmer? |  | To Identify project lead To meet with Baston PC To advertise for volunteers in grapevine | Unknown, removed 6/9/2026
| EE and Stowe road | Village gates/ planters - see note |  | Shelved until October |  | Unknown, removed 6/9/2026
| Deep in Kindness | Donate £100 - clerk to get donation details | Clerk |  | Community Engagement to provide details for donation funds to clerk | Unknown, removed 6/9/2026
| EEP | Worn surface and remove cable ties. Decision needed on how to manage goals and surface wear |  |  |  | Unknown, removed 6/9/2026
Note on C20: All existing documents handed back to Liz to pursue furnding. Permissions from LCC received pursue funding/finalise permissions/install Only 2 locations now required EE and Stowe Road